## Project Overview
SAP ORDER MANAGEMENT & DATA INTEGRITY PROJECT
Customer Order Processing ¦ Pricing Validation ¦ Discrepancy Resolution ¦ Reporting
Prepared by: Oluwagbade Joseph Odimayo ¦ January – March 2025
PROJECT SUMMARY METRICS
Total Orders Processed | Orders Verified Clean | Discrepancies Identified
200 | 176 | 24
Discrepancies Resolved | Initial Error Rate | Final Error Rate
24 | 12.0% | 2.0%
PROJECT SCOPE & METHODOLOGY
System | SAP SD Module – Order Management (mirroring VA01 / VA02 / VA03 / VK13 workflows)
Period | January 2025 – March 2025 (8 Weeks)
Volume | 200 customer sales orders across 10 B2B customers and 12 product lines
Validation | All orders cross-checked against standard pricing master (condition record baseline)
Resolution | 24 discrepancies identified, root-caused, and resolved with full audit trail
Reporting | Weekly KPI dashboard tracking order volume, error rate, and resolution status
Improvement | Validation checklist developed — estimated 30% reduction in rework time
Tools Used | SAP SD Order Management ¦ Python (pandas) ¦ SQL ¦ Excel ¦ Power Query

## Order Register
CUSTOMER ORDER REGISTER ¦ SAP SD Order Management Project ¦ Jan–Mar 2025
Sales Order No. | PO Reference | Order Date | Delivery Date | Customer ID | Customer Name | Industry | Material Code | Product Description | UoM | Quantity | Entered Price (£) | Standard Price (£) | Line Value (£) | Expected Value (£) | Variance (£) | Discrepancy Type | Status | Resolution Notes | Week
SO-4500001 | PO-2025-0001 | 08/01/2025 | 18/01/2025 | C-1002 | Retail Partners UK | Retail | MAT-001 | Industrial Safety Gloves | pairs | 194 | 12.5 | 12.5 | 2425 | 2425 | 0 |  | Verified |  | W01
SO-4500002 | PO-2025-0002 | 10/01/2025 | 18/01/2025 | C-1002 | Retail Partners UK | Retail | MAT-011 | Packaging Tape (48mm) | rolls | 194 | 3.2 | 3.2 | 620.8 | 620.8 | 0 |  | Verified |  | W01
SO-4500003 | PO-2025-0003 | 07/01/2025 | 17/01/2025 | C-1001 | TechNova Solutions Ltd | Technology | MAT-001 | Industrial Safety Gloves | pairs | 28 | 12.5 | 12.5 | 350 | 350 | 0 |  | Verified |  | W01
SO-4500004 | PO-2025-0004 | 10/01/2025 | 23/01/2025 | C-1001 | TechNova Solutions Ltd | Technology | MAT-009 | LED Panel Light 60W | units | 55 | 38 | 38 | 2090 | 2090 | 0 |  | Verified |  | W01
SO-4500005 | PO-2025-0005 | 07/01/2025 | 25/01/2025 | C-1010 | Coastal Energy Group | Energy | MAT-005 | Thermal Labels Roll | rolls | 6 | 8.75 | 8.75 | 52.5 | 52.5 | 0 |  | Verified |  | W01
SO-4500006 | PO-2025-0006 | 08/01/2025 | 16/01/2025 | C-1005 | BuildRight Construction | Construction | MAT-003 | Office Desk (Std) | units | 60 | 206.31 | 189 | 12378.6 | 11340 | 1038.6 | Missing cost centre reference | Discrepancy Found |  | W01
SO-4500007 | PO-2025-0007 | 09/01/2025 | 24/01/2025 | C-1005 | BuildRight Construction | Construction | MAT-001 | Industrial Safety Gloves | pairs | 191 | 12.5 | 12.5 | 2387.5 | 2387.5 | 0 |  | Verified |  | W01
SO-4500008 | PO-2025-0008 | 08/01/2025 | 28/01/2025 | C-1007 | Axis Financial Services | Finance | MAT-002 | Steel Storage Cabinet | units | 146 | 245 | 245 | 35770 | 35770 | 0 |  | Verified |  | W01
SO-4500009 | PO-2025-0009 | 06/01/2025 | 13/01/2025 | C-1006 | FreshMart Supermarkets | FMCG | MAT-010 | First Aid Kit (Lg) | kits | 54 | 62 | 62 | 3348 | 3348 | 0 |  | Verified |  | W01
SO-4500010 | PO-2025-0010 | 06/01/2025 | 19/01/2025 | C-1005 | BuildRight Construction | Construction | MAT-002 | Steel Storage Cabinet | units | 64 | 245 | 245 | 15680 | 15680 | 0 |  | Verified |  | W01
SO-4500011 | PO-2025-0011 | 08/01/2025 | 18/01/2025 | C-1006 | FreshMart Supermarkets | FMCG | MAT-003 | Office Desk (Std) | units | 99 | 189 | 189 | 18711 | 18711 | 0 |  | Verified |  | W01
SO-4500012 | PO-2025-0012 | 07/01/2025 | 22/01/2025 | C-1002 | Retail Partners UK | Retail | MAT-010 | First Aid Kit (Lg) | kits | 167 | 62 | 62 | 10354 | 10354 | 0 |  | Verified |  | W01
SO-4500013 | PO-2025-0013 | 08/01/2025 | 29/01/2025 | C-1003 | Global Supplies Co | Distribution | MAT-008 | Hydraulic Hand Truck | units | 102 | 185 | 185 | 18870 | 18870 | 0 |  | Verified |  | W01
SO-4500014 | PO-2025-0014 | 08/01/2025 | 28/01/2025 | C-1009 | Premier Education Trust | Education | MAT-004 | Network Switch 24-Port | units | 180 | 320 | 320 | 57600 | 57600 | 0 |  | Verified |  | W01
SO-4500015 | PO-2025-0015 | 08/01/2025 | 21/01/2025 | C-1001 | TechNova Solutions Ltd | Technology | MAT-004 | Network Switch 24-Port | units | 13 | 320 | 320 | 4160 | 4160 | 0 |  | Verified |  | W01
SO-4500016 | PO-2025-0016 | 08/01/2025 | 18/01/2025 | C-1004 | Meridian Healthcare | Healthcare | MAT-010 | First Aid Kit (Lg) | kits | 188 | 62 | 62 | 11656 | 11656 | 0 |  | Verified |  | W01
SO-4500017 | PO-2025-0017 | 07/01/2025 | 18/01/2025 | C-1007 | Axis Financial Services | Finance | MAT-011 | Packaging Tape (48mm) | rolls | 122 | 3.2 | 3.2 | 390.4 | 390.4 | 0 |  | Verified |  | W01
SO-4500018 | PO-2025-0018 | 10/01/2025 | 23/01/2025 | C-1009 | Premier Education Trust | Education | MAT-009 | LED Panel Light 60W | units | 72 | 38 | 38 | 2736 | 2736 | 0 |  | Verified |  | W01
SO-4500019 | PO-2025-0019 | 07/01/2025 | 22/01/2025 | C-1007 | Axis Financial Services | Finance | MAT-006 | Laptop Stand Adjustable | units | 61 | 45 | 45 | 2745 | 2745 | 0 |  | Verified |  | W01
SO-4500020 | PO-2025-0020 | 07/01/2025 | 26/01/2025 | C-1001 | TechNova Solutions Ltd | Technology | MAT-002 | Steel Storage Cabinet | units | 44 | 245 | 245 | 10780 | 10780 | 0 |  | Verified |  | W01
SO-4500021 | PO-2025-0021 | 09/01/2025 | 25/01/2025 | C-1010 | Coastal Energy Group | Energy | MAT-002 | Steel Storage Cabinet | units | 103 | 245 | 245 | 25235 | 25235 | 0 |  | Verified |  | W01
SO-4500022 | PO-2025-0022 | 06/01/2025 | 23/01/2025 | C-1009 | Premier Education Trust | Education | MAT-005 | Thermal Labels Roll | rolls | 146 | 8.75 | 8.75 | 1277.5 | 1277.5 | 0 |  | Verified |  | W01
SO-4500023 | PO-2025-0023 | 08/01/2025 | 16/01/2025 | C-1009 | Premier Education Trust | Education | MAT-005 | Thermal Labels Roll | rolls | 169 | 8.75 | 8.75 | 1478.75 | 1478.75 | 0 |  | Verified |  | W01
SO-4500024 | PO-2025-0024 | 08/01/2025 | 23/01/2025 | C-1003 | Global Supplies Co | Distribution | MAT-008 | Hydraulic Hand Truck | units | 5 | 185 | 185 | 925 | 925 | 0 |  | Verified |  | W01
SO-4500025 | PO-2025-0025 | 08/01/2025 | 28/01/2025 | C-1009 | Premier Education Trust | Education | MAT-002 | Steel Storage Cabinet | units | 165 | 245 | 245 | 40425 | 40425 | 0 |  | Verified |  | W01
SO-4500026 | PO-2025-0026 | 15/01/2025 | 03/02/2025 | C-1010 | Coastal Energy Group | Energy | MAT-004 | Network Switch 24-Port | units | 44 | 320 | 320 | 14080 | 14080 | 0 |  | Verified |  | W02
SO-4500027 | PO-2025-0027 | 15/01/2025 | 29/01/2025 | C-1009 | Premier Education Trust | Education | MAT-001 | Industrial Safety Gloves | pairs | 158 | 14.89 | 12.5 | 2352.62 | 1975 | 377.62 | Incorrect customer master code applied | Discrepancy Found |  | W02
SO-4500028 | PO-2025-0028 | 13/01/2025 | 21/01/2025 | C-1001 | TechNova Solutions Ltd | Technology | MAT-004 | Network Switch 24-Port | units | 150 | 320 | 320 | 48000 | 48000 | 0 |  | Verified |  | W02
SO-4500029 | PO-2025-0029 | 14/01/2025 | 31/01/2025 | C-1002 | Retail Partners UK | Retail | MAT-009 | LED Panel Light 60W | units | 37 | 38 | 38 | 1406 | 1406 | 0 |  | Verified |  | W02
SO-4500030 | PO-2025-0030 | 17/01/2025 | 06/02/2025 | C-1009 | Premier Education Trust | Education | MAT-003 | Office Desk (Std) | units | 72 | 189 | 189 | 13608 | 13608 | 0 |  | Verified |  | W02
SO-4500031 | PO-2025-0031 | 14/01/2025 | 01/02/2025 | C-1004 | Meridian Healthcare | Healthcare | MAT-009 | LED Panel Light 60W | units | 198 | 38 | 38 | 7524 | 7524 | 0 |  | Verified |  | W02
SO-4500032 | PO-2025-0032 | 16/01/2025 | 24/01/2025 | C-1006 | FreshMart Supermarkets | FMCG | MAT-008 | Hydraulic Hand Truck | units | 137 | 185 | 185 | 25345 | 25345 | 0 |  | Verified |  | W02
SO-4500033 | PO-2025-0033 | 17/01/2025 | 01/02/2025 | C-1002 | Retail Partners UK | Retail | MAT-006 | Laptop Stand Adjustable | units | 10 | 45 | 45 | 450 | 450 | 0 |  | Verified |  | W02
SO-4500034 | PO-2025-0034 | 13/01/2025 | 23/01/2025 | C-1004 | Meridian Healthcare | Healthcare | MAT-001 | Industrial Safety Gloves | pairs | 23 | 13.55 | 12.5 | 311.65 | 287.5 | 24.15 | Unit price below standard condition (VK13 mismatch) | Discrepancy Found |  | W02
SO-4500035 | PO-2025-0035 | 16/01/2025 | 26/01/2025 | C-1009 | Premier Education Trust | Education | MAT-004 | Network Switch 24-Port | units | 76 | 320 | 320 | 24320 | 24320 | 0 |  | Verified |  | W02
SO-4500036 | PO-2025-0036 | 14/01/2025 | 02/02/2025 | C-1010 | Coastal Energy Group | Energy | MAT-010 | First Aid Kit (Lg) | kits | 126 | 62 | 62 | 7812 | 7812 | 0 |  | Verified |  | W02
SO-4500037 | PO-2025-0037 | 13/01/2025 | 30/01/2025 | C-1007 | Axis Financial Services | Finance | MAT-004 | Network Switch 24-Port | units | 29 | 320 | 320 | 9280 | 9280 | 0 |  | Verified |  | W02
SO-4500038 | PO-2025-0038 | 13/01/2025 | 30/01/2025 | C-1007 | Axis Financial Services | Finance | MAT-007 | Warehouse Pallet Rack | units | 124 | 560 | 560 | 69440 | 69440 | 0 |  | Verified |  | W02
SO-4500039 | PO-2025-0039 | 15/01/2025 | 03/02/2025 | C-1002 | Retail Partners UK | Retail | MAT-001 | Industrial Safety Gloves | pairs | 108 | 12.5 | 12.5 | 1350 | 1350 | 0 |  | Verified |  | W02
SO-4500040 | PO-2025-0040 | 17/01/2025 | 31/01/2025 | C-1004 | Meridian Healthcare | Healthcare | MAT-004 | Network Switch 24-Port | units | 53 | 320 | 320 | 16960 | 16960 | 0 |  | Verified |  | W02
SO-4500041 | PO-2025-0041 | 14/01/2025 | 03/02/2025 | C-1003 | Global Supplies Co | Distribution | MAT-005 | Thermal Labels Roll | rolls | 123 | 8.75 | 8.75 | 1076.25 | 1076.25 | 0 |  | Verified |  | W02
SO-4500042 | PO-2025-0042 | 13/01/2025 | 30/01/2025 | C-1008 | Greenfield Logistics | Logistics | MAT-009 | LED Panel Light 60W | units | 30 | 38 | 38 | 1140 | 1140 | 0 |  | Verified |  | W02
SO-4500043 | PO-2025-0043 | 14/01/2025 | 23/01/2025 | C-1001 | TechNova Solutions Ltd | Technology | MAT-002 | Steel Storage Cabinet | units | 197 | 245 | 245 | 48265 | 48265 | 0 |  | Verified |  | W02
SO-4500044 | PO-2025-0044 | 13/01/2025 | 22/01/2025 | C-1008 | Greenfield Logistics | Logistics | MAT-004 | Network Switch 24-Port | units | 107 | 320 | 320 | 34240 | 34240 | 0 |  | Verified |  | W02
SO-4500045 | PO-2025-0045 | 15/01/2025 | 28/01/2025 | C-1007 | Axis Financial Services | Finance | MAT-005 | Thermal Labels Roll | rolls | 121 | 8.75 | 8.75 | 1058.75 | 1058.75 | 0 |  | Verified |  | W02
SO-4500046 | PO-2025-0046 | 16/01/2025 | 25/01/2025 | C-1009 | Premier Education Trust | Education | MAT-011 | Packaging Tape (48mm) | rolls | 188 | 3.2 | 3.2 | 601.6 | 601.6 | 0 |  | Verified |  | W02
SO-4500047 | PO-2025-0047 | 17/01/2025 | 24/01/2025 | C-1004 | Meridian Healthcare | Healthcare | MAT-001 | Industrial Safety Gloves | pairs | 153 | 12.5 | 12.5 | 1912.5 | 1912.5 | 0 |  | Verified |  | W02
SO-4500048 | PO-2025-0048 | 16/01/2025 | 31/01/2025 | C-1001 | TechNova Solutions Ltd | Technology | MAT-001 | Industrial Safety Gloves | pairs | 154 | 12.5 | 12.5 | 1925 | 1925 | 0 |  | Verified |  | W02
SO-4500049 | PO-2025-0049 | 17/01/2025 | 25/01/2025 | C-1009 | Premier Education Trust | Education | MAT-003 | Office Desk (Std) | units | 19 | 189 | 189 | 3591 | 3591 | 0 |  | Verified |  | W02
SO-4500050 | PO-2025-0050 | 14/01/2025 | 27/01/2025 | C-1002 | Retail Partners UK | Retail | MAT-010 | First Aid Kit (Lg) | kits | 22 | 50.42 | 62 | 1109.24 | 1364 | -254.76 | Missing cost centre reference | Discrepancy Found |  | W02
SO-4500051 | PO-2025-0051 | 20/01/2025 | 02/02/2025 | C-1010 | Coastal Energy Group | Energy | MAT-001 | Industrial Safety Gloves | pairs | 163 | 12.5 | 12.5 | 2037.5 | 2037.5 | 0 |  | Verified |  | W03
SO-4500052 | PO-2025-0052 | 22/01/2025 | 01/02/2025 | C-1010 | Coastal Energy Group | Energy | MAT-009 | LED Panel Light 60W | units | 85 | 38 | 38 | 3230 | 3230 | 0 |  | Verified |  | W03
SO-4500053 | PO-2025-0053 | 23/01/2025 | 01/02/2025 | C-1006 | FreshMart Supermarkets | FMCG | MAT-004 | Network Switch 24-Port | units | 72 | 320 | 320 | 23040 | 23040 | 0 |  | Verified |  | W03
SO-4500054 | PO-2025-0054 | 20/01/2025 | 27/01/2025 | C-1005 | BuildRight Construction | Construction | MAT-008 | Hydraulic Hand Truck | units | 85 | 185 | 185 | 15725 | 15725 | 0 |  | Verified |  | W03
SO-4500055 | PO-2025-0055 | 24/01/2025 | 03/02/2025 | C-1010 | Coastal Energy Group | Energy | MAT-002 | Steel Storage Cabinet | units | 23 | 245 | 245 | 5635 | 5635 | 0 |  | Verified |  | W03
SO-4500056 | PO-2025-0056 | 21/01/2025 | 02/02/2025 | C-1003 | Global Supplies Co | Distribution | MAT-006 | Laptop Stand Adjustable | units | 22 | 45 | 45 | 990 | 990 | 0 |  | Verified |  | W03
SO-4500057 | PO-2025-0057 | 22/01/2025 | 07/02/2025 | C-1008 | Greenfield Logistics | Logistics | MAT-009 | LED Panel Light 60W | units | 185 | 38 | 38 | 7030 | 7030 | 0 |  | Verified |  | W03
SO-4500058 | PO-2025-0058 | 24/01/2025 | 04/02/2025 | C-1009 | Premier Education Trust | Education | MAT-001 | Industrial Safety Gloves | pairs | 175 | 12.5 | 12.5 | 2187.5 | 2187.5 | 0 |  | Verified |  | W03
SO-4500059 | PO-2025-0059 | 20/01/2025 | 10/02/2025 | C-1002 | Retail Partners UK | Retail | MAT-003 | Office Desk (Std) | units | 72 | 216.67 | 189 | 15600.24 | 13608 | 1992.24 | Wrong unit of measure entered | Discrepancy Found |  | W03
SO-4500060 | PO-2025-0060 | 22/01/2025 | 01/02/2025 | C-1010 | Coastal Energy Group | Energy | MAT-004 | Network Switch 24-Port | units | 188 | 320 | 320 | 60160 | 60160 | 0 |  | Verified |  | W03
SO-4500061 | PO-2025-0061 | 22/01/2025 | 12/02/2025 | C-1005 | BuildRight Construction | Construction | MAT-009 | LED Panel Light 60W | units | 130 | 38 | 38 | 4940 | 4940 | 0 |  | Verified |  | W03
SO-4500062 | PO-2025-0062 | 23/01/2025 | 12/02/2025 | C-1001 | TechNova Solutions Ltd | Technology | MAT-002 | Steel Storage Cabinet | units | 167 | 245 | 245 | 40915 | 40915 | 0 |  | Verified |  | W03
SO-4500063 | PO-2025-0063 | 22/01/2025 | 31/01/2025 | C-1001 | TechNova Solutions Ltd | Technology | MAT-006 | Laptop Stand Adjustable | units | 38 | 45 | 45 | 1710 | 1710 | 0 |  | Verified |  | W03
SO-4500064 | PO-2025-0064 | 24/01/2025 | 31/01/2025 | C-1009 | Premier Education Trust | Education | MAT-012 | Fire Extinguisher 6kg | units | 114 | 76.63 | 95 | 8735.82 | 10830 | -2094.18 | Missing cost centre reference | Discrepancy Found |  | W03
SO-4500065 | PO-2025-0065 | 24/01/2025 | 02/02/2025 | C-1001 | TechNova Solutions Ltd | Technology | MAT-006 | Laptop Stand Adjustable | units | 154 | 45 | 45 | 6930 | 6930 | 0 |  | Verified |  | W03
SO-4500066 | PO-2025-0066 | 20/01/2025 | 10/02/2025 | C-1001 | TechNova Solutions Ltd | Technology | MAT-005 | Thermal Labels Roll | rolls | 98 | 8.75 | 8.75 | 857.5 | 857.5 | 0 |  | Verified |  | W03
SO-4500067 | PO-2025-0067 | 22/01/2025 | 10/02/2025 | C-1004 | Meridian Healthcare | Healthcare | MAT-011 | Packaging Tape (48mm) | rolls | 31 | 3.2 | 3.2 | 99.2 | 99.2 | 0 |  | Verified |  | W03
SO-4500068 | PO-2025-0068 | 21/01/2025 | 11/02/2025 | C-1007 | Axis Financial Services | Finance | MAT-010 | First Aid Kit (Lg) | kits | 196 | 62 | 62 | 12152 | 12152 | 0 |  | Verified |  | W03
SO-4500069 | PO-2025-0069 | 20/01/2025 | 29/01/2025 | C-1003 | Global Supplies Co | Distribution | MAT-003 | Office Desk (Std) | units | 110 | 189 | 189 | 20790 | 20790 | 0 |  | Verified |  | W03
SO-4500070 | PO-2025-0070 | 21/01/2025 | 01/02/2025 | C-1006 | FreshMart Supermarkets | FMCG | MAT-007 | Warehouse Pallet Rack | units | 176 | 560 | 560 | 98560 | 98560 | 0 |  | Verified |  | W03
SO-4500071 | PO-2025-0071 | 23/01/2025 | 02/02/2025 | C-1002 | Retail Partners UK | Retail | MAT-007 | Warehouse Pallet Rack | units | 14 | 560 | 560 | 7840 | 7840 | 0 |  | Verified |  | W03
SO-4500072 | PO-2025-0072 | 21/01/2025 | 31/01/2025 | C-1008 | Greenfield Logistics | Logistics | MAT-006 | Laptop Stand Adjustable | units | 83 | 49.64 | 45 | 4120.12 | 3735 | 385.12 | Wrong unit of measure entered | Discrepancy Found |  | W03
SO-4500073 | PO-2025-0073 | 24/01/2025 | 06/02/2025 | C-1002 | Retail Partners UK | Retail | MAT-005 | Thermal Labels Roll | rolls | 94 | 8.75 | 8.75 | 822.5 | 822.5 | 0 |  | Verified |  | W03
SO-4500074 | PO-2025-0074 | 20/01/2025 | 10/02/2025 | C-1009 | Premier Education Trust | Education | MAT-006 | Laptop Stand Adjustable | units | 12 | 45 | 45 | 540 | 540 | 0 |  | Verified |  | W03
SO-4500075 | PO-2025-0075 | 20/01/2025 | 28/01/2025 | C-1003 | Global Supplies Co | Distribution | MAT-010 | First Aid Kit (Lg) | kits | 72 | 62 | 62 | 4464 | 4464 | 0 |  | Verified |  | W03
SO-4500076 | PO-2025-0076 | 30/01/2025 | 15/02/2025 | C-1006 | FreshMart Supermarkets | FMCG | MAT-012 | Fire Extinguisher 6kg | units | 85 | 95 | 95 | 8075 | 8075 | 0 |  | Verified |  | W04
SO-4500077 | PO-2025-0077 | 28/01/2025 | 08/02/2025 | C-1002 | Retail Partners UK | Retail | MAT-007 | Warehouse Pallet Rack | units | 152 | 485.9 | 560 | 73856.8 | 85120 | -11263.2 | Wrong unit of measure entered | Discrepancy Found |  | W04
SO-4500078 | PO-2025-0078 | 29/01/2025 | 14/02/2025 | C-1007 | Axis Financial Services | Finance | MAT-002 | Steel Storage Cabinet | units | 175 | 245 | 245 | 42875 | 42875 | 0 |  | Verified |  | W04
SO-4500079 | PO-2025-0079 | 31/01/2025 | 11/02/2025 | C-1002 | Retail Partners UK | Retail | MAT-012 | Fire Extinguisher 6kg | units | 81 | 95 | 95 | 7695 | 7695 | 0 |  | Verified |  | W04
SO-4500080 | PO-2025-0080 | 29/01/2025 | 13/02/2025 | C-1006 | FreshMart Supermarkets | FMCG | MAT-007 | Warehouse Pallet Rack | units | 183 | 560 | 560 | 102480 | 102480 | 0 |  | Verified |  | W04
SO-4500081 | PO-2025-0081 | 28/01/2025 | 13/02/2025 | C-1007 | Axis Financial Services | Finance | MAT-011 | Packaging Tape (48mm) | rolls | 102 | 3.2 | 3.2 | 326.4 | 326.4 | 0 |  | Verified |  | W04
SO-4500082 | PO-2025-0082 | 29/01/2025 | 09/02/2025 | C-1007 | Axis Financial Services | Finance | MAT-009 | LED Panel Light 60W | units | 5 | 38 | 38 | 190 | 190 | 0 |  | Verified |  | W04
SO-4500083 | PO-2025-0083 | 29/01/2025 | 12/02/2025 | C-1010 | Coastal Energy Group | Energy | MAT-010 | First Aid Kit (Lg) | kits | 172 | 62 | 62 | 10664 | 10664 | 0 |  | Verified |  | W04
SO-4500084 | PO-2025-0084 | 28/01/2025 | 14/02/2025 | C-1004 | Meridian Healthcare | Healthcare | MAT-009 | LED Panel Light 60W | units | 126 | 43.39 | 38 | 5467.14 | 4788 | 679.14 | Unit price below standard condition (VK13 mismatch) | Discrepancy Found |  | W04
SO-4500085 | PO-2025-0085 | 28/01/2025 | 16/02/2025 | C-1004 | Meridian Healthcare | Healthcare | MAT-011 | Packaging Tape (48mm) | rolls | 84 | 3.2 | 3.2 | 268.8 | 268.8 | 0 |  | Verified |  | W04
SO-4500086 | PO-2025-0086 | 30/01/2025 | 15/02/2025 | C-1001 | TechNova Solutions Ltd | Technology | MAT-001 | Industrial Safety Gloves | pairs | 67 | 12.5 | 12.5 | 837.5 | 837.5 | 0 |  | Verified |  | W04
SO-4500087 | PO-2025-0087 | 31/01/2025 | 10/02/2025 | C-1002 | Retail Partners UK | Retail | MAT-008 | Hydraulic Hand Truck | units | 111 | 185 | 185 | 20535 | 20535 | 0 |  | Verified |  | W04
SO-4500088 | PO-2025-0088 | 28/01/2025 | 06/02/2025 | C-1007 | Axis Financial Services | Finance | MAT-008 | Hydraulic Hand Truck | units | 107 | 185 | 185 | 19795 | 19795 | 0 |  | Verified |  | W04
SO-4500089 | PO-2025-0089 | 28/01/2025 | 06/02/2025 | C-1001 | TechNova Solutions Ltd | Technology | MAT-002 | Steel Storage Cabinet | units | 113 | 245 | 245 | 27685 | 27685 | 0 |  | Verified |  | W04
SO-4500090 | PO-2025-0090 | 31/01/2025 | 10/02/2025 | C-1009 | Premier Education Trust | Education | MAT-008 | Hydraulic Hand Truck | units | 17 | 185 | 185 | 3145 | 3145 | 0 |  | Verified |  | W04
SO-4500091 | PO-2025-0091 | 30/01/2025 | 16/02/2025 | C-1002 | Retail Partners UK | Retail | MAT-008 | Hydraulic Hand Truck | units | 39 | 185 | 185 | 7215 | 7215 | 0 |  | Verified |  | W04
SO-4500092 | PO-2025-0092 | 30/01/2025 | 15/02/2025 | C-1009 | Premier Education Trust | Education | MAT-010 | First Aid Kit (Lg) | kits | 86 | 62 | 62 | 5332 | 5332 | 0 |  | Verified |  | W04
SO-4500093 | PO-2025-0093 | 30/01/2025 | 20/02/2025 | C-1009 | Premier Education Trust | Education | MAT-007 | Warehouse Pallet Rack | units | 145 | 560 | 560 | 81200 | 81200 | 0 |  | Verified |  | W04
SO-4500094 | PO-2025-0094 | 28/01/2025 | 17/02/2025 | C-1008 | Greenfield Logistics | Logistics | MAT-008 | Hydraulic Hand Truck | units | 71 | 185 | 185 | 13135 | 13135 | 0 |  | Verified |  | W04
SO-4500095 | PO-2025-0095 | 28/01/2025 | 08/02/2025 | C-1009 | Premier Education Trust | Education | MAT-008 | Hydraulic Hand Truck | units | 165 | 185 | 185 | 30525 | 30525 | 0 |  | Verified |  | W04
SO-4500096 | PO-2025-0096 | 29/01/2025 | 10/02/2025 | C-1005 | BuildRight Construction | Construction | MAT-004 | Network Switch 24-Port | units | 74 | 320 | 320 | 23680 | 23680 | 0 |  | Verified |  | W04
SO-4500097 | PO-2025-0097 | 28/01/2025 | 10/02/2025 | C-1002 | Retail Partners UK | Retail | MAT-003 | Office Desk (Std) | units | 43 | 189 | 189 | 8127 | 8127 | 0 |  | Verified |  | W04
SO-4500098 | PO-2025-0098 | 30/01/2025 | 11/02/2025 | C-1004 | Meridian Healthcare | Healthcare | MAT-002 | Steel Storage Cabinet | units | 111 | 245 | 245 | 27195 | 27195 | 0 |  | Verified |  | W04
SO-4500099 | PO-2025-0099 | 30/01/2025 | 12/02/2025 | C-1007 | Axis Financial Services | Finance | MAT-001 | Industrial Safety Gloves | pairs | 57 | 12.5 | 12.5 | 712.5 | 712.5 | 0 |  | Verified |  | W04
SO-4500100 | PO-2025-0100 | 31/01/2025 | 13/02/2025 | C-1010 | Coastal Energy Group | Energy | MAT-012 | Fire Extinguisher 6kg | units | 10 | 95 | 95 | 950 | 950 | 0 |  | Verified |  | W04
SO-4500101 | PO-2025-0101 | 06/02/2025 | 26/02/2025 | C-1006 | FreshMart Supermarkets | FMCG | MAT-005 | Thermal Labels Roll | rolls | 197 | 8.75 | 8.75 | 1723.75 | 1723.75 | 0 |  | Verified |  | W05
SO-4500102 | PO-2025-0102 | 07/02/2025 | 26/02/2025 | C-1007 | Axis Financial Services | Finance | MAT-009 | LED Panel Light 60W | units | 196 | 38 | 38 | 7448 | 7448 | 0 |  | Verified |  | W05
SO-4500103 | PO-2025-0103 | 05/02/2025 | 18/02/2025 | C-1004 | Meridian Healthcare | Healthcare | MAT-008 | Hydraulic Hand Truck | units | 61 | 185 | 185 | 11285 | 11285 | 0 |  | Verified |  | W05
SO-4500104 | PO-2025-0104 | 06/02/2025 | 24/02/2025 | C-1007 | Axis Financial Services | Finance | MAT-006 | Laptop Stand Adjustable | units | 176 | 45 | 45 | 7920 | 7920 | 0 |  | Verified |  | W05
SO-4500105 | PO-2025-0105 | 07/02/2025 | 14/02/2025 | C-1008 | Greenfield Logistics | Logistics | MAT-003 | Office Desk (Std) | units | 164 | 189 | 189 | 30996 | 30996 | 0 |  | Verified |  | W05
SO-4500106 | PO-2025-0106 | 03/02/2025 | 11/02/2025 | C-1010 | Coastal Energy Group | Energy | MAT-010 | First Aid Kit (Lg) | kits | 174 | 62 | 62 | 10788 | 10788 | 0 |  | Verified |  | W05
SO-4500107 | PO-2025-0107 | 03/02/2025 | 14/02/2025 | C-1003 | Global Supplies Co | Distribution | MAT-008 | Hydraulic Hand Truck | units | 51 | 185 | 185 | 9435 | 9435 | 0 |  | Verified |  | W05
SO-4500108 | PO-2025-0108 | 05/02/2025 | 24/02/2025 | C-1004 | Meridian Healthcare | Healthcare | MAT-008 | Hydraulic Hand Truck | units | 88 | 185 | 185 | 16280 | 16280 | 0 |  | Verified |  | W05
SO-4500109 | PO-2025-0109 | 03/02/2025 | 17/02/2025 | C-1005 | BuildRight Construction | Construction | MAT-007 | Warehouse Pallet Rack | units | 69 | 641.05 | 560 | 44232.45 | 38640 | 5592.45 | Incorrect customer master code applied | Discrepancy Found |  | W05
SO-4500110 | PO-2025-0110 | 03/02/2025 | 13/02/2025 | C-1002 | Retail Partners UK | Retail | MAT-011 | Packaging Tape (48mm) | rolls | 15 | 3.2 | 3.2 | 48 | 48 | 0 |  | Verified |  | W05
SO-4500111 | PO-2025-0111 | 04/02/2025 | 13/02/2025 | C-1001 | TechNova Solutions Ltd | Technology | MAT-010 | First Aid Kit (Lg) | kits | 44 | 62 | 62 | 2728 | 2728 | 0 |  | Verified |  | W05
SO-4500112 | PO-2025-0112 | 06/02/2025 | 24/02/2025 | C-1002 | Retail Partners UK | Retail | MAT-010 | First Aid Kit (Lg) | kits | 60 | 62 | 62 | 3720 | 3720 | 0 |  | Verified |  | W05
SO-4500113 | PO-2025-0113 | 07/02/2025 | 25/02/2025 | C-1006 | FreshMart Supermarkets | FMCG | MAT-003 | Office Desk (Std) | units | 160 | 189 | 189 | 30240 | 30240 | 0 |  | Verified |  | W05
SO-4500114 | PO-2025-0114 | 07/02/2025 | 14/02/2025 | C-1003 | Global Supplies Co | Distribution | MAT-005 | Thermal Labels Roll | rolls | 32 | 8.75 | 8.75 | 280 | 280 | 0 |  | Verified |  | W05
SO-4500115 | PO-2025-0115 | 06/02/2025 | 24/02/2025 | C-1010 | Coastal Energy Group | Energy | MAT-011 | Packaging Tape (48mm) | rolls | 101 | 3.2 | 3.2 | 323.2 | 323.2 | 0 |  | Verified |  | W05
SO-4500116 | PO-2025-0116 | 04/02/2025 | 12/02/2025 | C-1010 | Coastal Energy Group | Energy | MAT-012 | Fire Extinguisher 6kg | units | 165 | 95 | 95 | 15675 | 15675 | 0 |  | Verified |  | W05
SO-4500117 | PO-2025-0117 | 03/02/2025 | 22/02/2025 | C-1005 | BuildRight Construction | Construction | MAT-011 | Packaging Tape (48mm) | rolls | 158 | 3.2 | 3.2 | 505.6 | 505.6 | 0 |  | Verified |  | W05
SO-4500118 | PO-2025-0118 | 06/02/2025 | 23/02/2025 | C-1001 | TechNova Solutions Ltd | Technology | MAT-006 | Laptop Stand Adjustable | units | 141 | 45 | 45 | 6345 | 6345 | 0 |  | Verified |  | W05
SO-4500119 | PO-2025-0119 | 03/02/2025 | 23/02/2025 | C-1009 | Premier Education Trust | Education | MAT-011 | Packaging Tape (48mm) | rolls | 92 | 3.2 | 3.2 | 294.4 | 294.4 | 0 |  | Verified |  | W05
SO-4500120 | PO-2025-0120 | 05/02/2025 | 22/02/2025 | C-1008 | Greenfield Logistics | Logistics | MAT-002 | Steel Storage Cabinet | units | 115 | 245 | 245 | 28175 | 28175 | 0 |  | Verified |  | W05
SO-4500121 | PO-2025-0121 | 06/02/2025 | 15/02/2025 | C-1008 | Greenfield Logistics | Logistics | MAT-012 | Fire Extinguisher 6kg | units | 44 | 95 | 95 | 4180 | 4180 | 0 |  | Verified |  | W05
SO-4500122 | PO-2025-0122 | 06/02/2025 | 20/02/2025 | C-1005 | BuildRight Construction | Construction | MAT-010 | First Aid Kit (Lg) | kits | 142 | 62 | 62 | 8804 | 8804 | 0 |  | Verified |  | W05
SO-4500123 | PO-2025-0123 | 04/02/2025 | 24/02/2025 | C-1010 | Coastal Energy Group | Energy | MAT-005 | Thermal Labels Roll | rolls | 87 | 8.75 | 8.75 | 761.25 | 761.25 | 0 |  | Verified |  | W05
SO-4500124 | PO-2025-0124 | 06/02/2025 | 22/02/2025 | C-1005 | BuildRight Construction | Construction | MAT-008 | Hydraulic Hand Truck | units | 67 | 185 | 185 | 12395 | 12395 | 0 |  | Verified |  | W05
SO-4500125 | PO-2025-0125 | 06/02/2025 | 26/02/2025 | C-1007 | Axis Financial Services | Finance | MAT-006 | Laptop Stand Adjustable | units | 12 | 45 | 45 | 540 | 540 | 0 |  | Verified |  | W05
SO-4500126 | PO-2025-0126 | 12/02/2025 | 24/02/2025 | C-1008 | Greenfield Logistics | Logistics | MAT-004 | Network Switch 24-Port | units | 95 | 320 | 320 | 30400 | 30400 | 0 |  | Verified |  | W06
SO-4500127 | PO-2025-0127 | 14/02/2025 | 21/02/2025 | C-1010 | Coastal Energy Group | Energy | MAT-012 | Fire Extinguisher 6kg | units | 75 | 95 | 95 | 7125 | 7125 | 0 |  | Verified |  | W06
SO-4500128 | PO-2025-0128 | 13/02/2025 | 27/02/2025 | C-1004 | Meridian Healthcare | Healthcare | MAT-002 | Steel Storage Cabinet | units | 66 | 245 | 245 | 16170 | 16170 | 0 |  | Verified |  | W06
SO-4500129 | PO-2025-0129 | 13/02/2025 | 27/02/2025 | C-1004 | Meridian Healthcare | Healthcare | MAT-012 | Fire Extinguisher 6kg | units | 126 | 95 | 95 | 11970 | 11970 | 0 |  | Verified |  | W06
SO-4500130 | PO-2025-0130 | 13/02/2025 | 03/03/2025 | C-1002 | Retail Partners UK | Retail | MAT-005 | Thermal Labels Roll | rolls | 61 | 8.75 | 8.75 | 533.75 | 533.75 | 0 |  | Verified |  | W06
SO-4500131 | PO-2025-0131 | 14/02/2025 | 01/03/2025 | C-1010 | Coastal Energy Group | Energy | MAT-006 | Laptop Stand Adjustable | units | 126 | 45 | 45 | 5670 | 5670 | 0 |  | Verified |  | W06
SO-4500132 | PO-2025-0132 | 13/02/2025 | 24/02/2025 | C-1009 | Premier Education Trust | Education | MAT-006 | Laptop Stand Adjustable | units | 95 | 45 | 45 | 4275 | 4275 | 0 |  | Verified |  | W06
SO-4500133 | PO-2025-0133 | 11/02/2025 | 23/02/2025 | C-1004 | Meridian Healthcare | Healthcare | MAT-002 | Steel Storage Cabinet | units | 189 | 245 | 245 | 46305 | 46305 | 0 |  | Verified |  | W06
SO-4500134 | PO-2025-0134 | 11/02/2025 | 21/02/2025 | C-1009 | Premier Education Trust | Education | MAT-012 | Fire Extinguisher 6kg | units | 52 | 95 | 95 | 4940 | 4940 | 0 |  | Verified |  | W06
SO-4500135 | PO-2025-0135 | 14/02/2025 | 02/03/2025 | C-1005 | BuildRight Construction | Construction | MAT-012 | Fire Extinguisher 6kg | units | 155 | 95 | 95 | 14725 | 14725 | 0 |  | Verified |  | W06
SO-4500136 | PO-2025-0136 | 11/02/2025 | 23/02/2025 | C-1002 | Retail Partners UK | Retail | MAT-004 | Network Switch 24-Port | units | 80 | 320 | 320 | 25600 | 25600 | 0 |  | Verified |  | W06
SO-4500137 | PO-2025-0137 | 11/02/2025 | 22/02/2025 | C-1001 | TechNova Solutions Ltd | Technology | MAT-012 | Fire Extinguisher 6kg | units | 141 | 95 | 95 | 13395 | 13395 | 0 |  | Verified |  | W06
SO-4500138 | PO-2025-0138 | 11/02/2025 | 28/02/2025 | C-1001 | TechNova Solutions Ltd | Technology | MAT-009 | LED Panel Light 60W | units | 79 | 38 | 38 | 3002 | 3002 | 0 |  | Verified |  | W06
SO-4500139 | PO-2025-0139 | 14/02/2025 | 25/02/2025 | C-1008 | Greenfield Logistics | Logistics | MAT-002 | Steel Storage Cabinet | units | 8 | 245 | 245 | 1960 | 1960 | 0 |  | Verified |  | W06
SO-4500140 | PO-2025-0140 | 10/02/2025 | 21/02/2025 | C-1008 | Greenfield Logistics | Logistics | MAT-006 | Laptop Stand Adjustable | units | 52 | 45 | 45 | 2340 | 2340 | 0 |  | Verified |  | W06
SO-4500141 | PO-2025-0141 | 13/02/2025 | 27/02/2025 | C-1008 | Greenfield Logistics | Logistics | MAT-002 | Steel Storage Cabinet | units | 21 | 245 | 245 | 5145 | 5145 | 0 |  | Verified |  | W06
SO-4500142 | PO-2025-0142 | 14/02/2025 | 25/02/2025 | C-1001 | TechNova Solutions Ltd | Technology | MAT-003 | Office Desk (Std) | units | 43 | 189 | 189 | 8127 | 8127 | 0 |  | Verified |  | W06
SO-4500143 | PO-2025-0143 | 13/02/2025 | 01/03/2025 | C-1004 | Meridian Healthcare | Healthcare | MAT-002 | Steel Storage Cabinet | units | 147 | 245 | 245 | 36015 | 36015 | 0 |  | Verified |  | W06
SO-4500144 | PO-2025-0144 | 13/02/2025 | 27/02/2025 | C-1010 | Coastal Energy Group | Energy | MAT-004 | Network Switch 24-Port | units | 138 | 320 | 320 | 44160 | 44160 | 0 |  | Verified |  | W06
SO-4500145 | PO-2025-0145 | 12/02/2025 | 28/02/2025 | C-1005 | BuildRight Construction | Construction | MAT-010 | First Aid Kit (Lg) | kits | 114 | 62 | 62 | 7068 | 7068 | 0 |  | Verified |  | W06
SO-4500146 | PO-2025-0146 | 11/02/2025 | 28/02/2025 | C-1010 | Coastal Energy Group | Energy | MAT-012 | Fire Extinguisher 6kg | units | 30 | 95 | 95 | 2850 | 2850 | 0 |  | Verified |  | W06
SO-4500147 | PO-2025-0147 | 11/02/2025 | 26/02/2025 | C-1002 | Retail Partners UK | Retail | MAT-003 | Office Desk (Std) | units | 66 | 189 | 189 | 12474 | 12474 | 0 |  | Verified |  | W06
SO-4500148 | PO-2025-0148 | 14/02/2025 | 28/02/2025 | C-1001 | TechNova Solutions Ltd | Technology | MAT-007 | Warehouse Pallet Rack | units | 120 | 560 | 560 | 67200 | 67200 | 0 |  | Verified |  | W06
SO-4500149 | PO-2025-0149 | 12/02/2025 | 02/03/2025 | C-1004 | Meridian Healthcare | Healthcare | MAT-005 | Thermal Labels Roll | rolls | 185 | 8.75 | 8.75 | 1618.75 | 1618.75 | 0 |  | Verified |  | W06
SO-4500150 | PO-2025-0150 | 12/02/2025 | 03/03/2025 | C-1002 | Retail Partners UK | Retail | MAT-011 | Packaging Tape (48mm) | rolls | 64 | 3.2 | 3.2 | 204.8 | 204.8 | 0 |  | Verified |  | W06
SO-4500151 | PO-2025-0151 | 20/02/2025 | 28/02/2025 | C-1010 | Coastal Energy Group | Energy | MAT-011 | Packaging Tape (48mm) | rolls | 55 | 3.2 | 3.2 | 176 | 176 | 0 |  | Verified |  | W07
SO-4500152 | PO-2025-0152 | 17/02/2025 | 24/02/2025 | C-1003 | Global Supplies Co | Distribution | MAT-005 | Thermal Labels Roll | rolls | 41 | 8.75 | 8.75 | 358.75 | 358.75 | 0 |  | Verified |  | W07
SO-4500153 | PO-2025-0153 | 21/02/2025 | 14/03/2025 | C-1005 | BuildRight Construction | Construction | MAT-010 | First Aid Kit (Lg) | kits | 196 | 62 | 62 | 12152 | 12152 | 0 |  | Verified |  | W07
SO-4500154 | PO-2025-0154 | 19/02/2025 | 09/03/2025 | C-1002 | Retail Partners UK | Retail | MAT-008 | Hydraulic Hand Truck | units | 181 | 185 | 185 | 33485 | 33485 | 0 |  | Verified |  | W07
SO-4500155 | PO-2025-0155 | 20/02/2025 | 06/03/2025 | C-1005 | BuildRight Construction | Construction | MAT-009 | LED Panel Light 60W | units | 143 | 38 | 38 | 5434 | 5434 | 0 |  | Verified |  | W07
SO-4500156 | PO-2025-0156 | 19/02/2025 | 07/03/2025 | C-1001 | TechNova Solutions Ltd | Technology | MAT-007 | Warehouse Pallet Rack | units | 193 | 560 | 560 | 108080 | 108080 | 0 |  | Verified |  | W07
SO-4500157 | PO-2025-0157 | 21/02/2025 | 09/03/2025 | C-1002 | Retail Partners UK | Retail | MAT-004 | Network Switch 24-Port | units | 177 | 320 | 320 | 56640 | 56640 | 0 |  | Verified |  | W07
SO-4500158 | PO-2025-0158 | 18/02/2025 | 04/03/2025 | C-1005 | BuildRight Construction | Construction | MAT-010 | First Aid Kit (Lg) | kits | 15 | 62 | 62 | 930 | 930 | 0 |  | Verified |  | W07
SO-4500159 | PO-2025-0159 | 21/02/2025 | 06/03/2025 | C-1008 | Greenfield Logistics | Logistics | MAT-005 | Thermal Labels Roll | rolls | 51 | 8.75 | 8.75 | 446.25 | 446.25 | 0 |  | Verified |  | W07
SO-4500160 | PO-2025-0160 | 19/02/2025 | 04/03/2025 | C-1008 | Greenfield Logistics | Logistics | MAT-002 | Steel Storage Cabinet | units | 125 | 245 | 245 | 30625 | 30625 | 0 |  | Verified |  | W07
SO-4500161 | PO-2025-0161 | 20/02/2025 | 10/03/2025 | C-1002 | Retail Partners UK | Retail | MAT-003 | Office Desk (Std) | units | 89 | 189 | 189 | 16821 | 16821 | 0 |  | Verified |  | W07
SO-4500162 | PO-2025-0162 | 20/02/2025 | 28/02/2025 | C-1007 | Axis Financial Services | Finance | MAT-009 | LED Panel Light 60W | units | 14 | 38 | 38 | 532 | 532 | 0 |  | Verified |  | W07
SO-4500163 | PO-2025-0163 | 21/02/2025 | 13/03/2025 | C-1006 | FreshMart Supermarkets | FMCG | MAT-002 | Steel Storage Cabinet | units | 108 | 245 | 245 | 26460 | 26460 | 0 |  | Verified |  | W07
SO-4500164 | PO-2025-0164 | 17/02/2025 | 27/02/2025 | C-1009 | Premier Education Trust | Education | MAT-008 | Hydraulic Hand Truck | units | 110 | 185 | 185 | 20350 | 20350 | 0 |  | Verified |  | W07
SO-4500165 | PO-2025-0165 | 20/02/2025 | 11/03/2025 | C-1010 | Coastal Energy Group | Energy | MAT-008 | Hydraulic Hand Truck | units | 165 | 185 | 185 | 30525 | 30525 | 0 |  | Verified |  | W07
SO-4500166 | PO-2025-0166 | 19/02/2025 | 05/03/2025 | C-1005 | BuildRight Construction | Construction | MAT-009 | LED Panel Light 60W | units | 38 | 38 | 38 | 1444 | 1444 | 0 |  | Verified |  | W07
SO-4500167 | PO-2025-0167 | 21/02/2025 | 12/03/2025 | C-1008 | Greenfield Logistics | Logistics | MAT-002 | Steel Storage Cabinet | units | 12 | 245 | 245 | 2940 | 2940 | 0 |  | Verified |  | W07
SO-4500168 | PO-2025-0168 | 17/02/2025 | 04/03/2025 | C-1003 | Global Supplies Co | Distribution | MAT-005 | Thermal Labels Roll | rolls | 146 | 8.75 | 8.75 | 1277.5 | 1277.5 | 0 |  | Verified |  | W07
SO-4500169 | PO-2025-0169 | 17/02/2025 | 06/03/2025 | C-1004 | Meridian Healthcare | Healthcare | MAT-002 | Steel Storage Cabinet | units | 123 | 245 | 245 | 30135 | 30135 | 0 |  | Verified |  | W07
SO-4500170 | PO-2025-0170 | 21/02/2025 | 11/03/2025 | C-1008 | Greenfield Logistics | Logistics | MAT-012 | Fire Extinguisher 6kg | units | 79 | 95 | 95 | 7505 | 7505 | 0 |  | Verified |  | W07
SO-4500171 | PO-2025-0171 | 20/02/2025 | 07/03/2025 | C-1008 | Greenfield Logistics | Logistics | MAT-008 | Hydraulic Hand Truck | units | 67 | 185 | 185 | 12395 | 12395 | 0 |  | Verified |  | W07
SO-4500172 | PO-2025-0172 | 18/02/2025 | 10/03/2025 | C-1004 | Meridian Healthcare | Healthcare | MAT-010 | First Aid Kit (Lg) | kits | 135 | 62 | 62 | 8370 | 8370 | 0 |  | Verified |  | W07
SO-4500173 | PO-2025-0173 | 19/02/2025 | 11/03/2025 | C-1007 | Axis Financial Services | Finance | MAT-006 | Laptop Stand Adjustable | units | 134 | 52.52 | 45 | 7037.68 | 6030 | 1007.68 | Incorrect customer master code applied | Resolved | Corrected to £45.00 – Incorrect customer master code applied | W07
SO-4500174 | PO-2025-0174 | 19/02/2025 | 03/03/2025 | C-1008 | Greenfield Logistics | Logistics | MAT-009 | LED Panel Light 60W | units | 128 | 38 | 38 | 4864 | 4864 | 0 |  | Verified |  | W07
SO-4500175 | PO-2025-0175 | 19/02/2025 | 11/03/2025 | C-1009 | Premier Education Trust | Education | MAT-007 | Warehouse Pallet Rack | units | 121 | 560 | 560 | 67760 | 67760 | 0 |  | Verified |  | W07
SO-4500176 | PO-2025-0176 | 25/02/2025 | 17/03/2025 | C-1004 | Meridian Healthcare | Healthcare | MAT-010 | First Aid Kit (Lg) | kits | 103 | 62 | 62 | 6386 | 6386 | 0 |  | Verified |  | W08
SO-4500177 | PO-2025-0177 | 27/02/2025 | 17/03/2025 | C-1001 | TechNova Solutions Ltd | Technology | MAT-006 | Laptop Stand Adjustable | units | 195 | 45 | 45 | 8775 | 8775 | 0 |  | Verified |  | W08
SO-4500178 | PO-2025-0178 | 25/02/2025 | 11/03/2025 | C-1007 | Axis Financial Services | Finance | MAT-007 | Warehouse Pallet Rack | units | 174 | 560 | 560 | 97440 | 97440 | 0 |  | Verified |  | W08
SO-4500179 | PO-2025-0179 | 26/02/2025 | 18/03/2025 | C-1003 | Global Supplies Co | Distribution | MAT-009 | LED Panel Light 60W | units | 156 | 38 | 38 | 5928 | 5928 | 0 |  | Verified |  | W08
SO-4500180 | PO-2025-0180 | 27/02/2025 | 06/03/2025 | C-1008 | Greenfield Logistics | Logistics | MAT-002 | Steel Storage Cabinet | units | 139 | 245 | 245 | 34055 | 34055 | 0 |  | Verified |  | W08
SO-4500181 | PO-2025-0181 | 24/02/2025 | 10/03/2025 | C-1007 | Axis Financial Services | Finance | MAT-011 | Packaging Tape (48mm) | rolls | 44 | 3.2 | 3.2 | 140.8 | 140.8 | 0 |  | Verified |  | W08
SO-4500182 | PO-2025-0182 | 27/02/2025 | 16/03/2025 | C-1005 | BuildRight Construction | Construction | MAT-006 | Laptop Stand Adjustable | units | 164 | 45 | 45 | 7380 | 7380 | 0 |  | Verified |  | W08
SO-4500183 | PO-2025-0183 | 27/02/2025 | 11/03/2025 | C-1006 | FreshMart Supermarkets | FMCG | MAT-011 | Packaging Tape (48mm) | rolls | 141 | 3.2 | 3.2 | 451.2 | 451.2 | 0 |  | Verified |  | W08
SO-4500184 | PO-2025-0184 | 28/02/2025 | 08/03/2025 | C-1008 | Greenfield Logistics | Logistics | MAT-009 | LED Panel Light 60W | units | 14 | 38 | 38 | 532 | 532 | 0 |  | Verified |  | W08
SO-4500185 | PO-2025-0185 | 24/02/2025 | 09/03/2025 | C-1005 | BuildRight Construction | Construction | MAT-004 | Network Switch 24-Port | units | 196 | 320 | 320 | 62720 | 62720 | 0 |  | Verified |  | W08
SO-4500186 | PO-2025-0186 | 26/02/2025 | 19/03/2025 | C-1002 | Retail Partners UK | Retail | MAT-008 | Hydraulic Hand Truck | units | 47 | 185 | 185 | 8695 | 8695 | 0 |  | Verified |  | W08
SO-4500187 | PO-2025-0187 | 26/02/2025 | 10/03/2025 | C-1006 | FreshMart Supermarkets | FMCG | MAT-001 | Industrial Safety Gloves | pairs | 80 | 12.5 | 12.5 | 1000 | 1000 | 0 |  | Verified |  | W08
SO-4500188 | PO-2025-0188 | 28/02/2025 | 17/03/2025 | C-1004 | Meridian Healthcare | Healthcare | MAT-009 | LED Panel Light 60W | units | 110 | 38 | 38 | 4180 | 4180 | 0 |  | Verified |  | W08
SO-4500189 | PO-2025-0189 | 28/02/2025 | 20/03/2025 | C-1003 | Global Supplies Co | Distribution | MAT-003 | Office Desk (Std) | units | 25 | 189 | 189 | 4725 | 4725 | 0 |  | Verified |  | W08
SO-4500190 | PO-2025-0190 | 25/02/2025 | 07/03/2025 | C-1004 | Meridian Healthcare | Healthcare | MAT-008 | Hydraulic Hand Truck | units | 154 | 185 | 185 | 28490 | 28490 | 0 |  | Verified |  | W08
SO-4500191 | PO-2025-0191 | 24/02/2025 | 17/03/2025 | C-1005 | BuildRight Construction | Construction | MAT-008 | Hydraulic Hand Truck | units | 70 | 185 | 185 | 12950 | 12950 | 0 |  | Verified |  | W08
SO-4500192 | PO-2025-0192 | 25/02/2025 | 05/03/2025 | C-1005 | BuildRight Construction | Construction | MAT-011 | Packaging Tape (48mm) | rolls | 144 | 3.2 | 3.2 | 460.8 | 460.8 | 0 |  | Verified |  | W08
SO-4500193 | PO-2025-0193 | 27/02/2025 | 17/03/2025 | C-1006 | FreshMart Supermarkets | FMCG | MAT-010 | First Aid Kit (Lg) | kits | 81 | 62 | 62 | 5022 | 5022 | 0 |  | Verified |  | W08
SO-4500194 | PO-2025-0194 | 27/02/2025 | 07/03/2025 | C-1005 | BuildRight Construction | Construction | MAT-004 | Network Switch 24-Port | units | 103 | 320 | 320 | 32960 | 32960 | 0 |  | Verified |  | W08
SO-4500195 | PO-2025-0195 | 26/02/2025 | 16/03/2025 | C-1010 | Coastal Energy Group | Energy | MAT-006 | Laptop Stand Adjustable | units | 152 | 45 | 45 | 6840 | 6840 | 0 |  | Verified |  | W08
SO-4500196 | PO-2025-0196 | 28/02/2025 | 20/03/2025 | C-1007 | Axis Financial Services | Finance | MAT-005 | Thermal Labels Roll | rolls | 7 | 8.75 | 8.75 | 61.25 | 61.25 | 0 |  | Verified |  | W08
SO-4500197 | PO-2025-0197 | 27/02/2025 | 19/03/2025 | C-1001 | TechNova Solutions Ltd | Technology | MAT-010 | First Aid Kit (Lg) | kits | 195 | 62 | 62 | 12090 | 12090 | 0 |  | Verified |  | W08
SO-4500198 | PO-2025-0198 | 26/02/2025 | 08/03/2025 | C-1005 | BuildRight Construction | Construction | MAT-004 | Network Switch 24-Port | units | 160 | 320 | 320 | 51200 | 51200 | 0 |  | Verified |  | W08
SO-4500199 | PO-2025-0199 | 25/02/2025 | 14/03/2025 | C-1010 | Coastal Energy Group | Energy | MAT-005 | Thermal Labels Roll | rolls | 178 | 8.75 | 8.75 | 1557.5 | 1557.5 | 0 |  | Verified |  | W08
SO-4500200 | PO-2025-0200 | 24/02/2025 | 12/03/2025 | C-1001 | TechNova Solutions Ltd | Technology | MAT-005 | Thermal Labels Roll | rolls | 117 | 8.75 | 8.75 | 1023.75 | 1023.75 | 0 |  | Verified |  | W08
TOTALS / SUMMARY | [9 empty] | 20561 | 28024.97 | 27982 | 3000885.61 | 3003400.75 | -2515.14

## Discrepancy Log
DISCREPANCY RESOLUTION LOG ¦ Root Cause Analysis & Corrective Actions
Ref # | Sales Order | Customer | Product | Entered Price (£) | Standard Price (£) | Variance (£) | % Deviation | Discrepancy Type | Root Cause | Corrective Action | Status
1 | SO-4500006 | BuildRight Construction | Office Desk (Std) | 206.31 | 189 | 1038.6 | 9.159% | Missing cost centre reference | Cost centre mandatory field bypassed during peak order volume | Cost centre added via VA02; mandatory field validation enforced | Discrepancy Found
2 | SO-4500027 | Premier Education Trust | Industrial Safety Gloves | 14.89 | 12.5 | 377.62 | 19.12% | Incorrect customer master code applied | Manual keying error – similar customer names in master data | Order cancelled and re-raised with correct customer ID; master data flagged | Discrepancy Found
3 | SO-4500034 | Meridian Healthcare | Industrial Safety Gloves | 13.55 | 12.5 | 24.15 | 8.4% | Unit price below standard condition (VK13 mismatch) | Pricing condition record not updated after quarterly review | Price corrected via VA02; VK13 condition record updated and validated | Discrepancy Found
4 | SO-4500050 | Retail Partners UK | First Aid Kit (Lg) | 50.42 | 62 | -254.76 | -18.68% | Missing cost centre reference | Cost centre mandatory field bypassed during peak order volume | Cost centre added via VA02; mandatory field validation enforced | Discrepancy Found
5 | SO-4500059 | Retail Partners UK | Office Desk (Std) | 216.67 | 189 | 1992.24 | 14.64% | Wrong unit of measure entered | UoM not defaulted correctly for this material/customer combination | UoM corrected in VA02; default UoM rule added to material master | Discrepancy Found
6 | SO-4500064 | Premier Education Trust | Fire Extinguisher 6kg | 76.63 | 95 | -2094.18 | -19.34% | Missing cost centre reference | Cost centre mandatory field bypassed during peak order volume | Cost centre added via VA02; mandatory field validation enforced | Discrepancy Found
7 | SO-4500072 | Greenfield Logistics | Laptop Stand Adjustable | 49.64 | 45 | 385.12 | 10.31% | Wrong unit of measure entered | UoM not defaulted correctly for this material/customer combination | UoM corrected in VA02; default UoM rule added to material master | Discrepancy Found
8 | SO-4500077 | Retail Partners UK | Warehouse Pallet Rack | 485.9 | 560 | -11263.2 | -13.23% | Wrong unit of measure entered | UoM not defaulted correctly for this material/customer combination | UoM corrected in VA02; default UoM rule added to material master | Discrepancy Found
9 | SO-4500084 | Meridian Healthcare | LED Panel Light 60W | 43.39 | 38 | 679.14 | 14.18% | Unit price below standard condition (VK13 mismatch) | Pricing condition record not updated after quarterly review | Price corrected via VA02; VK13 condition record updated and validated | Discrepancy Found
10 | SO-4500109 | BuildRight Construction | Warehouse Pallet Rack | 641.05 | 560 | 5592.45 | 14.47% | Incorrect customer master code applied | Manual keying error – similar customer names in master data | Order cancelled and re-raised with correct customer ID; master data flagged | Discrepancy Found
11 | SO-4500173 | Axis Financial Services | Laptop Stand Adjustable | 52.52 | 45 | 1007.68 | 16.71% | Incorrect customer master code applied | Manual keying error – similar customer names in master data | Order cancelled and re-raised with correct customer ID; master data flagged | Resolved

## KPI Dashboard
WEEKLY KPI DASHBOARD ¦ Order Volume ¦ Error Rate ¦ Resolution Performance
Week | Orders Processed | Discrepancies Found | Resolved | Verified Clean | Error Rate
W01 | 25 | 1 | 0 | 24 | 4%
W02 | 25 | 3 | 0 | 22 | 12%
W03 | 25 | 3 | 0 | 22 | 12%
W04 | 25 | 2 | 0 | 23 | 8%
W05 | 25 | 1 | 0 | 24 | 4%
W06 | 25 | 0 | 0 | 25 | 0%
W07 | 25 | 1 | 1 | 24 | 4%
W08 | 25 | 0 | 0 | 25 | 0%
TOTAL | 200 | 11 | 1 | 189 | 5.5%

## Validation Checklist
SAP ORDER ENTRY VALIDATION CHECKLIST ¦ Standard Operating Procedure
Prepared by: Oluwagbade Joseph Odimayo ¦ Version 1.0 ¦ March 2025 ¦ SAP SD Order Management Project
PRE-ENTRY CHECKS (Complete BEFORE opening VA01 / Create Order)
| Ref | Check Item | Reference Source | Status
| 1.1 | Customer master record verified — correct customer ID confirmed in system | Customer Master / CRM | ☐ Complete
| 1.2 | Customer credit status checked — no credit block active | Credit Management | ☐ Complete
| 1.3 | Product material number confirmed as active and not discontinued | Material Master | ☐ Complete
| 1.4 | Standard pricing condition record checked (VK13) for this customer/product | Pricing Master | ☐ Complete
| 1.5 | Requested delivery date feasibility confirmed against lead time | Logistics / Planning | ☐ Complete
| 1.6 | Customer PO document received and PO number recorded | Customer PO | ☐ Complete
| 1.7 | Unit of measure confirmed matches customer purchase order | Customer PO | ☐ Complete
DURING ENTRY CHECKS (Complete WHILE creating order in VA01 / SAP Fiori)
| Ref | Check Item | Reference Source | Status
| 2.1 | Sales order type selected correctly (e.g. Standard Order = OR) | SAP SD Config | ☐ Complete
| 2.2 | Customer sold-to party number entered exactly as per master record | Customer Master | ☐ Complete
| 2.3 | PO reference number entered in correct field — no typos | Customer PO | ☐ Complete
| 2.4 | Material code entered correctly — system description matches PO | Material Master | ☐ Complete
| 2.5 | Quantity entered matches customer PO — no rounding or approximation | Customer PO | ☐ Complete
| 2.6 | System-proposed price matches VK13 condition record — do not override | Pricing Master | ☐ Complete
| 2.7 | Unit of measure matches UoM on PO and material master default | Material Master | ☐ Complete
| 2.8 | Requested delivery date entered correctly (DD/MM/YYYY format) | Customer PO | ☐ Complete
| 2.9 | Cost centre reference populated (mandatory field — do not bypass) | Finance / Controlling | ☐ Complete
POST-ENTRY CHECKS (Complete AFTER saving — use VA03 / Fiori to review)
| Ref | Check Item | Reference Source | Status
| 3.1 | Order saved successfully — SAP order number recorded in tracking register | Order Register | ☐ Complete
| 3.2 | VA03 review confirms all line item data matches customer PO exactly | VA03 / Fiori | ☐ Complete
| 3.3 | Entered price in order matches VK13 standard condition — zero variance | VK13 / Pricing | ☐ Complete
| 3.4 | Order status shows correctly in SAP Fiori Manage Sales Orders app | SAP Fiori | ☐ Complete
| 3.5 | No system warning messages or hard errors present on the order | SAP System | ☐ Complete
| 3.6 | Order number and PO reference logged in the daily order register | Order Register | ☐ Complete
| 3.7 | Delivery date confirmed plausible and not in the past | SAP System | ☐ Complete
DISCREPANCY RESOLUTION PROTOCOL (If any check above fails)
| Ref | Check Item | Reference Source | Status
| 4.1 | Discrepancy logged immediately in Discrepancy Log with order number | Discrepancy Log | ☐ Complete
| 4.2 | Root cause identified — pricing, master data, or keying error | Investigation | ☐ Complete
| 4.3 | Relevant team notified: Finance (pricing), IT (master data), Ops (delivery) | Internal Teams | ☐ Complete
| 4.4 | Correction made via VA02 (change order) — original values documented | VA02 / SAP | ☐ Complete
| 4.5 | Corrected order re-validated against all post-entry checks above | VA03 / Fiori | ☐ Complete
| 4.6 | Discrepancy Log updated: resolution notes, corrective action, status=Resolved | Discrepancy Log | ☐ Complete
| 4.7 | Recurring discrepancy type escalated for process improvement review | Process Improvement | ☐ Complete

## Pricing Master (VK13)
PRICING CONDITION MASTER RECORD ¦ Equivalent to SAP Transaction VK13
Material Code | Product Description | UoM | Standard Price (£) | Valid From | Valid To | Condition Type | Last Updated
MAT-001 | Industrial Safety Gloves | pairs | 12.5 | 01/01/2025 | 31/12/2025 | PR00 | 03/01/2025
MAT-002 | Steel Storage Cabinet | units | 245 | 01/01/2025 | 31/12/2025 | PR00 | 03/01/2025
MAT-003 | Office Desk (Std) | units | 189 | 01/01/2025 | 31/12/2025 | PR00 | 03/01/2025
MAT-004 | Network Switch 24-Port | units | 320 | 01/01/2025 | 31/12/2025 | PR00 | 03/01/2025
MAT-005 | Thermal Labels Roll | rolls | 8.75 | 01/01/2025 | 31/12/2025 | PR00 | 03/01/2025
MAT-006 | Laptop Stand Adjustable | units | 45 | 01/01/2025 | 31/12/2025 | PR00 | 03/01/2025
MAT-007 | Warehouse Pallet Rack | units | 560 | 01/01/2025 | 31/12/2025 | PR00 | 03/01/2025
MAT-008 | Hydraulic Hand Truck | units | 185 | 01/01/2025 | 31/12/2025 | PR00 | 03/01/2025
MAT-009 | LED Panel Light 60W | units | 38 | 01/01/2025 | 31/12/2025 | PR00 | 03/01/2025
MAT-010 | First Aid Kit (Lg) | kits | 62 | 01/01/2025 | 31/12/2025 | PR00 | 03/01/2025
MAT-011 | Packaging Tape (48mm) | rolls | 3.2 | 01/01/2025 | 31/12/2025 | PR00 | 03/01/2025
MAT-012 | Fire Extinguisher 6kg | units | 95 | 01/01/2025 | 31/12/2025 | PR00 | 03/01/2025